## Time estimation
| ANGLER Technologies | Doc. Ref: 9.1: PC /D 06/1.0
| Standard Time Estimation Document | Date: 23-07-2026 | Page:1
Project : | BuildX - Vendora | Version History
Date: | 2026-07-23 | Version | Date | Man days Shared | Comments
Version: | 1 | 1 | 2026-07-23
Prepared By: | Santhiya/Aruna |  |  |  | Optimum Plan |  | Max. Plan
S.No | Modules | Task Split Estimate (Hrs) | Man Hours | Man Days | # of People | No. of Calendar Weeks | # of People | No. of Calendar Weeks | Milestone | Reusable / Part of Product road map | Comments
1 | System Study |  | 1 | 0.125 | 1 | 0.025 | 1 | 0.025
| Technical Study | 0
| Requirement gathering | 0
| Proposal and SRS preparation | 1 | [6 empty] | Y
| Learning Effort | 0
2 | Project Planning |  | 2 | 0.25 | 1 | 0.05 | 1 | 0.05
| Project Plan | 1
| Time estimation and Time line | 1
3 | Design and Development |  | 0 | 0 | 1 | 0 | 2 | 0
| High Level Design | 0
| Detailed Design | 0
4 | Home page & sub page design |  | 0 | 0 | 1 | 0 | 2 | 0
| Home page & sub page design | 0
5 | Visual Prototype |  | 160 | 20 | 1 | 4 | 2 | 2
| 40 | 160 | [6 empty] | Y
6 | Coding |  | 792 | 99 | 3 | 6.6 | 4 | 4.95 | Y |  | Coding tasks are split module-wise; every coding task is 16 hours or less.
| Project Setup & Architecture - Application environment and repository setup | 16 | [8 empty] | Existing product setup / customization
| Project Setup & Architecture - Database extensions and integration base configuration | 8 | [8 empty] | Existing product setup / customization
| Authentication & Access - Role and permission matrix customization | 14 | [8 empty] | Existing module customization
| Authentication & Access - Project, plant, finance and admin access controls | 14 | [8 empty] | Existing module customization
ERP Integration
| ERP Inbound Integration - API authentication and connection framework | 16 | [8 empty] | ERP API integration
| ERP Inbound Integration - Project master synchronization | 16 | [8 empty] | ERP API integration
| ERP Inbound Integration - Milestone master synchronization | 16 | [8 empty] | ERP API integration
| ERP Inbound Integration - Material and service master synchronization | 16 | [8 empty] | ERP API integration
| ERP Inbound Integration - Plant master synchronization | 12 | [8 empty] | ERP API integration
| ERP Inbound Integration - Material intent and requirement synchronization | 12 | [8 empty] | ERP API integration
| ERP Outbound Integration - Invoice status, acknowledgement and retry handling | 4 | [8 empty] | Two-way ERP API integration
| Project & Plant Management - Dynamic plant master and project mapping | 14 | [8 empty] | Customer-specific alteration
| Project & Plant Management - Plant active, hold, close and transaction validation | 14 | [8 empty] | Customer-specific alteration
Vendor Onboarding
| Vendor Onboarding - Client-specific vendor profile and compliance fields | 14 | [8 empty] | Existing vendor module customization
| Vendor Onboarding - Vendor to material/category mapping | 14 | [8 empty] | Existing vendor module customization
| Vendor Onboarding - Vendor to plant mapping and effective dates | 14 | [8 empty] | Existing vendor module customization
| Vendor Onboarding - Eligibility filtering, hold status and approval history | 14 | [8 empty] | Existing vendor module customization
RFQ
| Material Requirement - ERP intent display and plant request entry | 14 | [8 empty] | Customer-specific workflow
| Material Requirement - Approval, return, reject, hold and remarks workflow | 14 | [8 empty] | Customer-specific workflow
| Material Requirement - Attachments and split/group requirements into RFQ | 12 | [8 empty] | Customer-specific workflow
| RFQ Management - Create RFQ from approved requirements | 16 | [8 empty] | Existing RFQ module customization
| RFQ Management - Eligible vendor recommendation and exception handling | 14 | [8 empty] | Existing RFQ module customization
| RFQ Management - Approval, issue, status and response tracking | 14 | [8 empty] | Email / WhatsApp trigger included
| Quotation Management - Quotation entry, attachments and revision history | 16 | [8 empty] | Existing quotation module customization
| Quotation Management - Price, discount, tax, freight and landed value calculation | 16 | [8 empty] | Existing quotation module customization
| Quotation Management - Item-wise and vendor-wise commercial comparison | 16 | [8 empty] | Existing quotation module customization
| Vendor Selection - Recommendation, negotiated price and terms capture | 14 | [8 empty] | Customer-specific approval controls
| Vendor Selection - Non-L1 justification, approval, locking and re-approval | 14 | [8 empty] | Customer-specific approval controls
Purchase order
| Purchase Order - PO creation manually from approved vendor quotation | 16 | [8 empty] | Existing PO module customization
| Purchase Order - Approval, release, hold and vendor communication | 16 | [8 empty] | Existing PO module customization
| Purchase Order - Amendment versioning, re-approval and printable PO | 16 | [8 empty] | Existing PO module customization
GRN
| GRN Management - Manual plant/stores GRN entry against PO | 14 | [8 empty] | New/custom GRN workflow
| GRN Management - Partial receipts, multiple GRNs and quantity validation | 14 | [8 empty] | New/custom GRN workflow
| GRN Management - Damage/rejection, attachment, verification and PO status update | 12 | [8 empty] | New/custom GRN workflow
Invoice Management
| Invoice Management - Invoice PDF upload and invoice detail entry | 14 | [8 empty] | Customer-specific invoice workflow
| Invoice Management - PO/GRN linkage and duplicate invoice validation | 14 | [8 empty] | Customer-specific invoice workflow
| Invoice Management - Finance verification, hold/reject and Tally posting trigger | 14 | [8 empty] | Customer-specific invoice workflow
Tally Integration
| Tally Posting Integration - Connector, authentication and configuration | 16 | [8 empty] | Third-party Tally integration
| Tally Posting Integration - Ledger, GST and project cost-centre mapping | 16 | [8 empty] | Third-party Tally integration
| Tally Posting Integration - Purchase voucher/debit/credit payload and posting response | 16 | [8 empty] | Third-party Tally integration
| Tally Posting Integration - Idempotency, retry, reversal and reposting controls | 16 | [8 empty] | Third-party Tally integration
| Tally Status Sync - Voucher acknowledgement and posting status synchronization | 16 | [8 empty] | Two-way Tally integration
| Tally Status Sync - Payment status, paid amount, balance and reference sync | 16 | [8 empty] | Two-way Tally integration
Notification setup
| Email & WhatsApp - Provider configuration and communication templates | 16 | [8 empty] | SMTP/API + WhatsApp Business provider
| Email & WhatsApp - RFQ, PO and GRN notification triggers | 16 | [8 empty] | SMTP/API + WhatsApp Business provider
| Email & WhatsApp - Tally/payment alerts, delivery log and retry handling | 16 | [8 empty] | SMTP/API + WhatsApp Business provider
Dashboards & Reports
| Dashboards & Reports - Procurement dashboard and pipeline status | 16 | [8 empty] | Existing dashboard customization
| Dashboards & Reports - Requirement, RFQ, PO and GRN reports | 16 | [8 empty] | Existing report customization
| Dashboards & Reports - Invoice, payment, ageing, reconciliation and export reports | 16 | [8 empty] | Existing report customization
| Integration Admin - ERP/Tally status, error logs and manual retry | 14 | [8 empty] | Integration administration
| Integration Admin - Mapping configuration, reconciliation and audit history | 14 | [8 empty] | Integration administration
| Developer Testing - Module unit testing and validation scenarios | 14 | [8 empty] | Coding-level test coverage
| Developer Testing - ERP, Tally and communication integration testing | 12 | [8 empty] | Coding-level test coverage
| Stabilization - Workflow, UI and validation defect fixing | 16 | [8 empty] | Post-development stabilization
| Stabilization - ERP/Tally integration fixes and regression stabilization | 12 | [8 empty] | Post-development stabilization
7 | Code Review |  | 8 | 1 | 1 | 0.2 | 1 | 0.2
| Code Review | 8
8 | Testing & Implementation |  | 256 | 32 | 1 | 6.4 | 1 | 6.4 | Y
| Test Cases | 40
| Testing & Bug validation | 100
| Bug Closing | 40
| Additional Browsers testing | 40
| Security Testing - Mandatory | 20
| Performance Testing - Optional | 8
| User Manual | 8
9 | Project Release (Consider both test server & live server releases) |  | 8 | 1 | 1 | 0.2 | 1 | 0.2
| Client's Server configuration | 8
Data Migration / One time data import
Server Migration
User Training / Client Visits / After Release Support Efforts (if Required)
10 | Project Management |  | 9 | 1.125 | 1 | 0.225 | 1 | 0.225
| Telecall | 4
| Project Review (by PM) | 4
| PL Project briefing to testers, Team member clarifications, etc | 1
| Total time estimate(Hrs) | 1236 | 1236 |  |  | 17.7 |  | 14.05
| 10% Buffer | 123.6 | 123.6
| Total Hours | 1359.6 | 1359.6
| Total Man Days | 169.95 | 169.95
| Total man Months | 7.725 | 7.725
| Approximate Calendar Weeks | 14 to 16 weeks (Optimum); 11 to 13 weeks (Max.)
Disclaimers:
1 | The calendar weeks calculated is only a suggestion. Refer the next sheet for approximate calendar weeks calculation
2 | When the application is quite large or based on client priority, decide on going for phase releases and split the estimation format for phase releases like, including testing, release, project management hours for each releases
3 | Third-party integration coding for ERP, Tally, Email and WhatsApp is included in the Coding section. Licensing/subscription/message charges, provider approvals, and changes inside client ERP/Tally are excluded.
Risks:
The scope is vast and the efforts given are ballpark estimaiton only
Browser Compatibility with versions
• Chrome 118
Technology with versions
React JS + NodeJS
MySQL 7
Operating System(OS) Compatibility with versions
Windows Server 2012